## Sheet1 (hidden)
Booked
Complete
Cancelled
Need Assistance

## Legend & Summary
Dacorum Borough Council - Commercial Properties
Booked / In Progress
Cancelled survey requests
Assistance required by Dacorum, Incorrect Telephone numbers etc.
Complete surveys - Highlight once sent
| Management Surveys | ASR1 Requests | Spare Tab
Number of requests | 85 | 12 | 51
Complete | 0 | 10 | 0
Outstanding | 0 | 0 | 0
Booked | 0 | 0 | 0
Cancelled | 0 | 2 | 0
Need Assistance | 0 | 0 | 0

## Management Survey
Job Number | Name | Requestee | Survey Type | UPRN | Address | Post Code | NOTES / MISSED APPTS | Letter Sent | Access issues | Date received | Date Surveyed | Due Date | Survey sent | Status | Re-inspections 2026
G-17388 |  | Richard Tattersall | Management |  | 48 High Street | HP1 3AF | Appoint Booked |  |  |  | 2024-11-06 |  | 2024-11-29 | Complete
G-17572 |  | Richard Tattersall | Management |  | Adeyfield Community Centre | HP2 4EW | Appoint Booked |  | Revisit required - Booked in with Julie Banks for the 7th Aug |  | 2024-08-07 |  | 2025-08-20 | Complete
G-17887 |  | Richard Tattersall | Management |  | Bellgate Shopping Centre 1-38 | HP2 5SB | Appoint Booked |  | Not all areas available, revisit date DBC |  | TBC |  | 2025-04-29 | Complete
G-17256 |  | Richard Tattersall | Management |  | Bennetts End Community Centre | HP3 9LZ | Appoint Booked |  |  |  | 2024-10-28 |  | 2024-11-27 | Complete
G-17855 |  | Richard Tattersall | Management |  | Bennetsgate Shopping Centre 1-51 | HP3 8EW | Appoint Booked |  |  |  | 2025-02-03 |  | 2025-02-26 | Complete
G-17364 |  | Richard Tattersall | Management |  | Berkhampstead Civic Centre | HP4 3HB | Appoint Booked |  |  |  | 2024-11-05 |  | 2024-11-28 | Complete
G-17421 |  | Richard Tattersall | Management |  | Brickfields Ind Est 1-21 | HP2 7QA | Appoint Booked |  |  |  | 2024-11-08 |  | 2024-11-20 | Complete
G-17763 |  | Richard Tattersall | Management |  | Chaulden Adventure Playground | HP1 2NX | Appoint Booked |  |  |  | 2024-12-05 |  | 2024-12-17 | Complete
G-17372 |  | Richard Tattersall | Management |  | Chaulden Community Centre | HP1 2HX | Appoint Booked |  |  |  | 2024-11-05 |  | 2024-11-18 | Complete
G-17886 |  | Richard Tattersall | Management |  | Chaulden Shops | HP1 2HX | Appoint Booked |  |  |  | 2025-02-04 |  | 2025-02-19 | Complete
G-17389 |  | Richard Tattersall | Management |  | Cupid Green Depot (building A) | HP2 7BA | Appoint Booked |  |  |  | 2024-11-07 |  | 2024-11-19 | Complete
G-17390 |  | Richard Tattersall | Management |  | Cupid Green Depot (Buildings B&C) | HP2 7BA | Appoint Booked |  |  |  | 2024-11-06 |  | 2024-11-20 | Complete
G-17325 |  | Richard Tattersall | Management |  | Gadebridge Community Centre | HP1 3LG | Appoint Booked |  |  |  | 2024-11-01 |  | 2024-11-22 | Complete
G-17327 |  | Richard Tattersall | Management |  | Gadebridge Youth Centre | HP1 3LF | Appoint Booked |  |  |  | 2024-11-01 |  | 2024-11-19 | Complete
G-17289 |  | Richard Tattersall | Management |  | Grovehill Community Centre | HP2 6BJ | Appoint Booked |  |  |  | 2024-10-29 |  | 2024-11-10 | Complete
G-17643 |  | Richard Tattersall | Management |  | Heath Lane cemetery Chapel | HP1 1TS | Appoint Booked |  |  |  | 2024-12-06 |  | 2024-12-20 | Complete
G-17644 |  | Richard Tattersall | Management |  | Heath Lane cemetery Lodge | HP1 1TS | Appoint rebooked with Maria for the 3rd April |  | 6/12 Tenant of Lodge wouldn't allow access, rebook |  | 2025-04-03 |  | 2025-04-11 | Complete
G-19396 |  | Richard Tattersall | Management |  | Hemel Hempstead Bowls Club | HP1 1HR |  |  | No answer to various calls, emails. Chris Conley, put me in touch with Micheal Darke at the club who has booked this in for 9.30am on the 11th April |  | 2025-04-11 |  |  | Complete
G-17444 |  | Richard Tattersall | Management |  | High Street Green Sports Pavillion | HP2 7AR | Appoint Booked |  |  |  | 2024-11-08 |  | 2024-12-02 | Complete
G-17291 |  | Richard Tattersall | Management |  | Highfield Community Centre | HP2 5SB | Appoint Booked |  | Bar No access - Awaiting date and time we can access this area |  | 2025-05-15 |  | 2025-05-16 | Complete
G-17885 |  | Richard Tattersall | Management |  | Hobbs Hill Road Shops | HP3 9QG | Appoint Booked |  |  |  | 2025-01-28 |  | 2025-02-07 | Complete
G-19256 |  | Richard Tattersall | Management |  | Kingshill Cemetery Lodge | HP4 3UG | Appoint Booked |  |  |  | 2025-04-03 |  | 2025-04-11 | Complete
G-19257 |  | Richard Tattersall | Management |  | Kingshill Cemetery Workshop, Welfare Area & toilets | HP4 3UG | Appoint Booked |  |  |  | 2025-04-03 |  | 2025-04-11 | Complete
G-17445 |  | Richard Tattersall | Management |  | Leverstock Green Sports pavilion | HP3 8QG | Appoint Booked |  |  |  | 2024-11-11 |  | 2025-11-29 | Complete
G-18507 |  | Richard Tattersall | Management |  | Leverstock Green Village Centre Shops | HP3 8QG | Appoint Booked |  |  |  | 2025-02-05 |  | 2025-02-19 | Complete
G-17318 |  | Richard Tattersall | Management |  | Leverstock Green Village Hall | HP3 8QG | Appoint Booked |  | No access to library - Book revisit for a Thursday |  | TBC |  | 2025-04-28 | Complete
G-17446 |  | Richard Tattersall | Management |  | Nash Mills Recreation Area Shower & Toilet Facilities | HP3 9TE | Appoint Booked |  |  |  | 2024-12-02 |  | 2024-12-16 | Complete
G-18148 |  | Richard Tattersall | Management |  | Old Town Hall | HP1 3AE | Appoint Booked |  |  |  | 2025-02-10 |  | 2025-02-18 | Complete
G-19397 |  | Richard Tattersall | Management |  | Old Town Public Convenience | HP1 3AE | Appoint Booked |  | Tony Moore to have keys avaialable for us to collect from the Bowls Club in the morning |  | 2025-04-11 |  | 2025-04-29 | Complete
G-18146 |  | Richard Tattersall | Management |  | Queens Square Shopping Centre | HP2 4ES | Appoint Booked |  |  |  | 2025-02-11 |  | 2025-02-20 | Complete
G-18147 |  | Richard Tattersall | Management |  | Stoneycroft Shopping Centre | HP1 2QF | Appoint Booked |  |  |  | 2025-01-15 |  | 2025-02-04 | Complete
G-18292 |  | Richard Tattersall | Management |  | The Bury registry Office | HP1 1HR | Appoint Booked |  |  |  | 2025-02-12 |  | 2025-02-19 | Complete
G-17366 |  | Richard Tattersall | Management |  | The Centre in the Park | HP1 3AE | Appoint Booked |  |  |  | 2024-11-04 |  | 2024-12-05 | Complete
G-18293 |  | Richard Tattersall | Management |  | The Counting House | HP23 5TE | Appoint Booked |  |  |  | 2025-02-13 |  | 2025-02-27 | Complete
G-18508 |  | Richard Tattersall | Management |  | The Denes Shopping Centre | HP3 8AP | Appoint Booked |  |  |  | 2025-02-07 |  | 2025-03-03 | Complete
G-19398 |  | Richard Tattersall | Management |  | The Forge Car Park Public Convenience | HP23 5SH | Appoint Booked |  | Keysafe for access (1972) |  | 2025-04-11 |  | 2025-04-29 | Complete
G-18471 |  | Richard Tattersall | Management |  | The Gables ( Relate) | HP2 5HL | Appoint Booked |  |  |  | 2025-02-06 |  | 2025-02-18 | Complete
G-17854 |  | Richard Tattersall | Management |  | The Heights Shopping Centre | HP2 5NX | Appoint Booked |  |  |  | 2024-12-11 |  | 2025-01-07 | Complete
G-17365 |  | Richard Tattersall | Management |  | Tring community Centre | HP23 5EP | Appoint Booked |  |  |  | 2025-01-22 |  | 2025-02-03 | Complete
G-17640 |  | Richard Tattersall | Management |  | Tringford depot | HP23 4JL | Appoint Booked |  |  |  | 2025-02-07 |  | 2025-02-19 | Complete
G-17661 |  | Richard Tattersall | Management |  | Warners End community Centre | HP1 3QG | Appoint Booked |  |  |  | 2025-01-10 |  | 2025-01-22 | Complete
G-23387 |  | Richard Tattersall | Management |  | Wayside | HP2 7BA | Appoint Booked |  | Spoke to Tony Moore, tenant of property suffers with dementia. He will make contact to explain and come back to me when ready to schedule in |  | 2025-11-25 |  | 2025-12-09 | Complete
G-17329 |  | Richard Tattersall | Management |  | Woodhall farm Community Centre | HP2 7JX | Appoint Booked |  |  |  | 2024-11-19 |  | 2024-11-22 | Complete
G-19212 |  | Richard Tattersall | Management |  | Woodwells Cemetery Lodge | HP2 7LF | Appoint Booked |  |  |  | 2025-03-31 |  | 2025-04-10 | Complete
G-19211 |  | Richard Tattersall | Management |  | Woodwells Cemetery Office, toilets & Workshop | HP2 7LF | Appoint Booked |  |  |  | 2025-03-31 |  | 2025-04-09 | Complete
G-21250 |  | Richard Tattersall - Batch 2 | Management |  | Adeyfield Adventure Playground | HP2 4LW | Appoint Booked |  |  |  | 2025-07-15 |  | 2025-07-18 | Complete
G-21667 |  | Richard Tattersall - Batch 2 | Management |  | Apsley Community Centre | HP3 9SB | Appoint Booked |  |  |  | 2025-08-08 |  | 2025-09-03 | Complete
G-20911 |  | Richard Tattersall - Batch 2 | Management |  | Apsley Industrial Estate Units 1 to 16 | HP3 9XH | Appoint Booked |  |  |  | 2025-06-25 |  | 2025-07-16 | Complete
G-21571 |  | Richard Tattersall - Batch 2 | Management |  | Apsley Public Convenience | HP3 9RG | Appoint Booked |  |  |  | 2025-08-22 |  | 2025-09-05 | Complete
G-21251 |  | Richard Tattersall - Batch 2 | Management |  | Bennetts End Adventure Playground | HP3 8EQ | Appoint Booked |  |  |  | 2025-07-15 |  | 2025-07-22 | Complete
G-22039 |  | Richard Tattersall - Batch 2 | Management |  | Bennetts End Depot | HP3 8EN | Appoint Booked |  |  |  | 2025-08-29 |  | 2025-09-08 | Complete
G-20971 |  | Richard Tattersall - Batch 2 | Management |  | Charter Court / Beautyfull Beauty Room | WD4 9HR | Appoint Booked |  |  |  | 2025-07-10 |  | 2025-07-25 | Complete
G-21184 |  | Richard Tattersall - Batch 2 | Management |  | Charter Court / Kings Langley Parish Council | WD4 9HR | Appoint Booked |  |  |  | 2025-07-10 |  | 2025-07-25 | Complete
|  | Richard Tattersall - Batch 2 | Management |  | Coronation Fields Sports Pavilion | HP3 9UP |  |  | Property has had a Leak, survey not to be conducted until issue resolved and the pavilion is accesible again |  |  |  |  | Need Assistance
G-22113 |  | Richard Tattersall - Batch 2 | Management |  | Cupid Green Depot, Building D | HP2 7BA | Booked with Lee Coutney 4 & 5th Sep |  |  |  | 2025-09-05 |  | 2025-09-15 | Complete
G-22114 |  | Richard Tattersall - Batch 2 | Management |  | Cupid Green Depot, Building E | HP2 7BA | Booked with Lee Coutney 4 & 5th Sep |  |  |  | 2025-09-05 |  | 2025-09-15 | Complete
G-22116 |  | Richard Tattersall - Batch 2 | Management |  | Cupid Green Depot, Vehicle Wash | HP2 7BA | Booked with Lee Coutney 4 & 5th Sep |  |  |  | 2025-09-05 |  | 2025-09-15 | Complete
G-22117 |  | Richard Tattersall - Batch 2 | Management |  | Cupid Green Depot, Waste Yard | HP2 7BA | Booked with Lee Coutney 4 & 5th Sep |  |  |  | 2025-09-05 |  | 2025-09-15 | Complete
G-21362 |  | Richard Tattersall - Batch 2 | Management |  | Cupid Green Sports Pavilion | HP2 7BA |  |  |  |  | 2025-07-22 |  | 2025-08-01 | Complete
G-21339 |  | Richard Tattersall - Batch 2 | Management |  | Dacre House | HP2 4AA | Appoint Booked |  |  |  | 2025-07-21 |  | 2025-07-24 | Complete
G-21223 |  | Richard Tattersall - Batch 2 | Management |  | Grovehill and Woodhall Farm Adventure Playground | HP2 7BA | Appoint Booked |  |  |  | 2025-07-14 |  | 2025-07-18 | Complete
G-22010 |  | Richard Tattersall - Batch 2 | Management |  | Grovehill Sports Pavilion | HP2 6NH |  |  |  |  | 2025-08-28 |  | 2025-09-08 | Complete
G-21338 |  | Richard Tattersall - Batch 2 | Management |  | Grovehill Youth Centre | HP2 6BH | Appoint Booked |  |  |  | 2025-07-21 |  | 2025-08-04 | Complete
G-20939 |  | Richard Tattersall - Batch 2 | Management |  | Henry Wells Square Shops | HP2 6BJ | Appoint Booked |  |  |  | 2025-06-25 |  | 2025-07-14 | Complete
|  | Richard Tattersall - Batch 2 | Management |  | Lagley Meadow Sports Pavilion | HP4 3PE |  |  | Keys need to be located |  |  |  |  | Need Assistance
G-21942 |  | Richard Tattersall - Batch 2 | Management |  | Leverstock Green Public Convenience | HP3 8QG | Appoint Booked |  |  |  | 2025-08-22 |  | 2025-09-05 | Complete
G-22181 |  | Richard Tattersall - Batch 2 | Management |  | Leverstock Green Village Hall - Library | HP3 8QG | Appoint Booked |  |  |  | 2025-09-09 |  | 2025-09-16 | Complete
G-21195 |  | Richard Tattersall - Batch 2 | Management |  | Rossgate Shopping Centre numbers 1 to 33 (+ 4 garages) | HP1 3LG | Appoint Booked |  |  |  | 2025-07-11 |  | 2025-07-18 | Complete
G-22147 |  | Richard Tattersall - Batch 2 | Management |  | Silk Mill Shopping Centre | HP23 5EP | Appoint Booked |  |  |  | 2025-09-08 |  | 2025-09-16 | Complete
G-21634 |  | Richard Tattersall - Batch 2 | Management |  | The Bury Garages 1 - 7 (Numbered from Gadebridge Park) | HP1 1HR | Appoint Booked |  |  |  | 2025-08-06 |  | 2025-08-13 | Complete
G-23181 |  | Richard Tattersall - Batch 2 | Management |  | The Bury Garages 10 - 12 (Numbered from Gadebridge Park) | HP1 1HR | Unable to make contact to date: Tina has now returned to work and provided contact details to make an appointment: tina.ferris@dacorum.gov.uk: Tel - 07855 200562 |  | Emails sent, no response |  | 2025-11-12 |  | 2025-11-18 | Complete
G-22146 |  | Richard Tattersall - Batch 2 | Management |  | The Bury Garages 8 - 9 (Numbered from Gadebridge Park) | HP1 1HR | Appoint Booked |  |  |  | 2025-09-05 |  | 2025-09-15 | Complete
G-21633 |  | Richard Tattersall - Batch 2 | Management |  | The Bury Lodge (Dens) | HP1 1HT | Appoint Booked |  |  |  | 2025-08-06 |  | 2025-08-13 | Complete
G-21751 |  | Richard Tattersall - Batch 2 | Management |  | Trefoil House | HP3 9TE | Appoint Booked with Jess Rixon |  |  |  | 2025-08-12 |  | 2025-09-01 | Complete
G-21934 |  | Richard Tattersall - Batch 2 | Management |  | Tring Cemetery Chapel | HP23 4DH | Appoint Booked |  |  |  | 2025-08-21 |  | 2025-09-03 | Complete
G-21936 |  | Richard Tattersall - Batch 2 | Management |  | Tring Cemetery Lodge | HP23 4DH | Appoint Booked |  |  |  | 2025-08-21 |  | 2025-09-03 | Complete
G-21935 |  | Richard Tattersall - Batch 2 | Management |  | Tring Cemetery Staff Mess Room | HP23 4DH | Appoint Booked |  |  |  | 2025-08-21 |  | 2025-09-03 | Complete
G-21937 |  | Richard Tattersall - Batch 2 | Management |  | Tring Cemetery Visitor Toilets | HP23 4DH | Appoint Booked |  |  |  | 2025-08-21 |  | 2025-09-04 | Complete
G-22009 |  | Richard Tattersall - Batch 2 | Management |  | Velvet Lawn Sports Pavilion | HP4 2LN | Appoint Booked |  |  |  | 2025-08-27 |  | 2025-09-08 | Complete
G-21635 |  | Richard Tattersall - Batch 2 | Management |  | Victoria Hall | HP23 6AA | Appoint Booked |  |  |  | 2025-08-06 |  | 2025-08-20 | Complete
G-21660 |  | Richard Tattersall - Batch 2 | Management |  | Volunteer Centre | HP1 1DT | Appoint Booked with Kerry |  |  |  | 2025-08-07 |  | 2025-08-21 | Complete
G-21691 |  | Richard Tattersall - Batch 2 | Management |  | Walled Garden and Charter Tower | HP1 3AE | Appoint Booked |  |  |  | 2025-09-01 |  | 2025-09-03 | Complete
|  | Richard Tattersall - Batch 2 | Management |  | Warners End Sports Pavilion | HP1 3LA |  |  | Subject to arson attack, not currently required |  |  |  |  | Cancelled
G-21053 |  | Richard Tattersall - Batch 2 | Management |  | Water Gardens Car Park North | HP1 1EF | Appoint booked |  |  |  | 2025-07-02 |  | 2025-07-11 | Complete
G-21943 |  | Richard Tattersall - Batch 2 | Management |  | Water Lane Public Convenience | HP4 3FG | Appoint Booked |  |  |  | 2025-08-22 |  | 2025-09-05 | Complete

## ASR1 Requests
Job Number | Name | Requestee | Building Type | Survey Type | UPRN | Address | Post Code | Contact Number | NOTES / MISSED APPTS | Letter Sent | Access Issues | Date Received | Date Surveyed | Due Date | Survey Sent | Status
G-17422 |  | Richard Tattersall | Commercial | Management |  | Unit 10 Brickfield | HP2 7QA |  |  |  |  | 2024-10-29 | 2024-11-08 |  | 2024-11-20 | Complete
G-17792 |  | Tony Moore | Commercial | Refurbishment |  | 128-130 Bennetsgate | HP3 8DZ |  |  |  |  | 2024-12-04 | 2024-12-05 |  | 2024-12-10 | Complete
G17952 |  | Richard Tattersall | Commercial | Management |  | Grovehill Youth Centre | HP2 6BH |  |  |  |  | 2024-12-17 | 2024-12-23 |  | 2024-01-16 | Complete
|  | Jim Mitchell | Commercial | Refurbishment |  | House that jack built - Nursery | HP3 8EW |  | Spoke to Jim, he said to cancel request as the works have already been carried out | [6 empty] | Cancelled
G-18204 |  | Horace White | Commercial | Management |  | 1-2 Hammer Lane | HP2 4EU |  |  |  |  | 2025-01-16 | 2025-01-20 |  | 2025-01-22 | Complete
|  | Richard Tattersall | Commercial | Refurbishment |  | 14 Appsley Ind Est | HP3 9XH |  | Called to book in survey, Jim Mitchell advised that a survey had already been carried out and that this is not now required |  |  | 2025-01-09 |  |  |  | Cancelled
G-18816 |  | Tony Moore | Commercial | Refurbishment |  | 3 Queensway | HP1 1LS |  |  |  |  | 2025-02-28 | 2025-03-03 |  | 2025-03-06 | Complete
G-19978 |  | Jim Mitchell | Commercial | Refurbishment |  | Unit 8 Appsley | HP3 9XH |  |  |  |  | 2025-05-09 | 2025-05-13 |  | 2025-05-16 | Complete
G-19979 |  | Tony Moore | Commercial | Management |  | 52 Old Town | HP1 3AF |  |  |  |  | 2025-05-09 | 2025-05-14 |  | 2025-05-19 | Complete
G-19980 |  | Tony Moore | Commercial | Management |  | 100 Old Town | HP1 3AQ |  |  |  |  | 2025-05-09 | 2025-05-13 |  | 2025-05-16 | Complete
G-18293 Iss 3 |  | Tony Moore | Commercial | Refurbishment |  | The Counting House | HP1 1HH |  | Works being undertaken in the basement that was previously innaccesible, Tony asked us to attend to meet Orion on site to run through works and survey the area |  |  | 2025-08-27 | 2025-08-28 |  | 2025-09-01 | Complete
G-23025 |  | Richard Tattersall | Commercial | Refurbishment |  | Little Hay Golf Complex | HP3 0DT |  | Left Message & Sent email to Gearge Reid for access |  |  | 2025-10-24 | 2025-11-03 |  | 2025-11-12 | Complete

## Spare
Job Number | Name | Requestee | Work Type | Priority of works | UPRN | Address | Post Code | Contact Number | NOTES / MISSED APPTS | Letter Sent | Access Issues | Date Received | Date Surveyed | Due Date | Survey Sent | Status

## Re-Inspections 26
Job Number | Name | Requestee | Work Type | UPRN | Address | Post Code | NOTES / MISSED APPTS | Letter Sent | Access Issues | Date Received | Date Surveyed | Due Date | Survey Sent | Status
G-17256 |  | Richard Tattersall | Management |  | Bennetts End Community Centre | HP3 9LZ | Appoint Booked |  |  | 2024-11-27
G-17289 |  | Richard Tattersall | Management |  | Grovehill Community Centre | HP2 6BJ | Appoint Booked |  |  | 2024-11-10
G-17291 |  | Richard Tattersall | Management |  | Highfield Community Centre | HP2 5SB | Appoint Booked |  | Bar No access - Awaiting date and time we can access this area | 2025-05-20
G-17318 |  | Richard Tattersall | Management |  | Leverstock Green Village Hall | HP3 8QG | Appoint Booked |  | No access to library - Book revisit for a Thursday | 2025-04-25
G-17325 |  | Richard Tattersall | Management |  | Gadebridge Community Centre | HP1 3LG | Appoint Booked |  |  | 2024-11-27
G-17327 |  | Richard Tattersall | Management |  | Gadebridge Youth Centre | HP1 3LF | Appoint Booked |  |  | 2024-11-19
G-17329 |  | Richard Tattersall | Management |  | Woodhall farm Community Centre | HP2 7JX | Appoint Booked |  |  | 2024-11-22
G-17364 |  | Richard Tattersall | Management |  | Berkhampstead Civic Centre | HP4 3HB | Appoint Booked |  |  | 2024-11-28
G-17365 |  | Richard Tattersall | Management |  | Tring community Centre | HP23 5EP | Appoint Booked |  |  | 2025-02-06
G-17366 |  | Richard Tattersall | Management |  | The Centre in the Park | HP1 3AE | Appoint Booked |  |  | 2024-12-07
G-17372 |  | Richard Tattersall | Management |  | Chaulden Community Centre | HP1 2HX | Appoint Booked |  |  | 2024-12-10
G-17389 |  | Richard Tattersall | Management |  | Cupid Green Depot (building A) | HP2 7BA | Appoint Booked |  |  | 2024-11-19
G-17390 |  | Richard Tattersall | Management |  | Cupid Green Depot (Buildings B&C) | HP2 7BA | Appoint Booked |  |  | 2024-11-20
G-17421 |  | Richard Tattersall | Management |  | Brickfields Ind Est 1-21 | HP2 7QA | Appoint Booked |  |  | 2024-11-20
G-17444 |  | Richard Tattersall | Management |  | High Street Green Sports Pavillion | HP2 7AR | Appoint Booked |  |  | 2024-12-16
G-17445 |  | Richard Tattersall | Management |  | Leverstock Green Sports pavilion | HP3 8QG | Appoint Booked |  |  | 2024-11-29
G-17446 |  | Richard Tattersall | Management |  | Nash Mills Recreation Area Shower & Toilet Facilities | HP3 9TE | Appoint Booked |  |  | 2024-12-19
G-17572 |  | Richard Tattersall | Management |  | Adeyfield Community Centre | HP2 4EW | Appoint Booked |  | Revisit required - Booked in with Julie Banks for the 7th Aug | 2025-08-20
G-17640 |  | Richard Tattersall | Management |  | Tringford depot | HP23 4JL | Appoint Booked |  |  | 2025-02-19
G-17643 |  | Richard Tattersall | Management |  | Heath Lane cemetery Chapel | HP1 1TS | Appoint Booked |  |  | 2024-12-20
G-17644 |  | Richard Tattersall | Management |  | Heath Lane cemetery Lodge | HP1 1TS | Appoint rebooked with Maria for the 3rd April |  | 6/12 Tenant of Lodge wouldn't allow access, rebook | 2024-12-21
G-17661 |  | Richard Tattersall | Management |  | Warners End community Centre | HP1 3QG | Appoint Booked |  |  | 2025-01-22
G-17763 |  | Richard Tattersall | Management |  | Chaulden Adventure Playground | HP1 2NX | Appoint Booked |  |  | 2024-12-20
G-17854 |  | Richard Tattersall | Management |  | The Heights Shopping Centre | HP2 5NX | Appoint Booked |  |  | 2025-01-07
G-17855 |  | Richard Tattersall | Management |  | Bennetsgate Shopping Centre 1-51 | HP3 8EW | Appoint Booked |  |  | 2025-02-26
G-17885 |  | Richard Tattersall | Management |  | Hobbs Hill Road Shops | HP3 9QG | Appoint Booked |  |  | 2025-01-13
G-17886 |  | Richard Tattersall | Management |  | Chaulden Shops | HP1 2HX | Appoint Booked |  |  | 2025-02-19
G-17887 |  | Richard Tattersall | Management |  | Bellgate Shopping Centre 1-38 | HP2 5SB | Appoint Booked |  | Not all areas available, revisit date DBC | 2025-04-29
G-18146 |  | Richard Tattersall | Management |  | Queens Square Shopping Centre | HP2 4ES | Appoint Booked |  |  | 2025-02-19
G-18147 |  | Richard Tattersall | Management |  | Stoneycroft Shopping Centre | HP1 2QF | Appoint Booked |  |  | 2025-02-04
G-18148 |  | Richard Tattersall | Management |  | Old Town Hall | HP1 3AE | Appoint Booked |  |  | 2025-02-18
G-18292 |  | Richard Tattersall | Management |  | The Bury registry Office | HP1 1HR | Appoint Booked |  |  | 2025-02-19
G-18293 |  | Richard Tattersall | Management |  | The Counting House | HP23 5TE | Appoint Booked |  |  | 2025-09-01
G-18471 |  | Richard Tattersall | Management |  | The Gables ( Relate) | HP2 5HL | Appoint Booked |  |  | 2025-02-18
G-18507 |  | Richard Tattersall | Management |  | Leverstock Green Village Centre Shops | HP3 8QG | Appoint Booked |  |  | 2025-02-19
G-18508 |  | Richard Tattersall | Management |  | The Denes Shopping Centre | HP3 8AP | Appoint Booked |  |  | 2025-03-06
G-19211 |  | Richard Tattersall | Management |  | Woodwells Cemetery Office, toilets & Workshop | HP2 7LF | Appoint Booked |  |  | 2025-04-10
G-19212 |  | Richard Tattersall | Management |  | Woodwells Cemetery Lodge | HP2 7LF | Appoint Booked |  |  | 2025-04-09
G-19257 |  | Richard Tattersall | Management |  | Kingshill Cemetery Workshop, Welfare Area & toilets | HP4 3UG | Appoint Booked |  |  | 2025-04-10
G-19396 |  | Richard Tattersall | Management |  | Hemel Hempstead Bowls Club | HP1 1HR |  |  | No answer to various calls, emails. Chris Conley, put me in touch with Micheal Darke at the club who has booked this in for 9.30am on the 11th April | 2025-06-05
G-19397 |  | Richard Tattersall | Management |  | Old Town Public Convenience | HP1 3AE | Appoint Booked |  | Tony Moore to have keys avaialable for us to collect from the Bowls Club in the morning | 2025-04-29
G-19398 |  | Richard Tattersall | Management |  | The Forge Car Park Public Convenience | HP23 5SH | Appoint Booked |  | Keysafe for access (1972) | 2025-04-29
G-20911 |  | Richard Tattersall - Batch 2 | Management |  | Apsley Industrial Estate Units 1 to 16 | HP3 9XH | Appoint Booked |  |  | 2025-07-16
G-21053 |  | Richard Tattersall - Batch 2 | Management |  | Water Gardens Car Park North | HP1 1EF | Appoint booked |  |  | 2025-07-11
G-21195 |  | Richard Tattersall - Batch 2 | Management |  | Rossgate Shopping Centre numbers 1 to 33 (+ 4 garages) | HP1 3LG | Appoint Booked |  |  | 2025-07-17
G-21251 |  | Richard Tattersall - Batch 2 | Management |  | Bennetts End Adventure Playground | HP3 8EQ | Appoint Booked |  |  | 2025-07-18
G-21635 |  | Richard Tattersall - Batch 2 | Management |  | Victoria Hall | HP23 6AA | Appoint Booked |  |  | 2025-08-20
G-22039 |  | Richard Tattersall - Batch 2 | Management |  | Bennetts End Depot | HP3 8EN | Appoint Booked |  |  | 2025-09-08
G-22147 |  | Richard Tattersall - Batch 2 | Management |  | Silk Mill Shopping Centre | HP23 5EP | Appoint Booked |  |  | 2025-09-19
G-22181 |  | Richard Tattersall - Batch 2 | Management |  | Leverstock Green Village Hall - Library | HP3 8QG | Appoint Booked |  |  | 2025-09-16
G-23387 |  | Richard Tattersall | Management |  | Wayside | HP2 7BA | Appoint Booked |  | Spoke to Tony Moore, tenant of property suffers with dementia. He will make contact to explain and come back to me when ready to schedule in